## Template
|  | Phases: | Phase 1 name |  | Phase 2 name |  | Phase 3 name |  | Phase 4 name
|  |  | Hours | 1 | Hours | 1 | Hours | 1 | Hours | 1 | Total Hours | 4
Week
1 |  |  | Task | 1 | Task | 1 | Task | 1 | Task | 1 | Week 1 | 4
2 | [10 empty] | Week 2 | 0
| PSR#1 | Feb 14th
3 | [10 empty] | Week 3 | 0
Break | [10 empty] | Break | 0
4 | [10 empty] | Week 4 | 0
| PSR#2 | March 7th
5 | [10 empty] | Week 5 | 0
6 | [10 empty] | Week 6 | 0
| PSR#3 | March 21st
7 | [10 empty] | Week 7 | 0
8 | [10 empty] | Week 8 | 0
| PSR#4 | April 4th
9 | [10 empty] | Week 9 | 0
Break | [10 empty] | Break | 0
10 | [10 empty] | Week 10 | 0
| PSR#5 | April 25th

## Template with PreRelease
|  | Phases: | Research/Planning |  | Design/Prototyping |  | Production/Build |  | Launch/Community
|  |  | Hours | 12.5 | Hours | 46.5 | Hours | 56 | Hours | 41.5 | Total Hours | 156.5
Week
Pre | [10 empty] | PreRelease | 0
PrePSR
1 |  |  | Establish Hypothesis | 5 | [6 empty] | Week 1 | 14
|  |  | Research Near Space Satellites | 3 | Prototyping/CAD | 5 |  |  | Video Log 1 | 1
Break |  |  | Research Electrical Systems/Sensors | 1 | Prototyping/CAD | 5 | Electrical Test Build | 5 |  |  | Break | 16
[5 empty] | Prototyping/CAD | 3.5 |  |  | Curriculum Development | 1.5
Week 2 |  |  | Create Shopping List /Purchase Items | 2 | Finalize Design | 1.5 |  |  | Video Log 2 | 1 | Week 2 | 9
| PSR #1 | 2019-02-21 |  |  | Approve Design | 3 |  |  | Curriculum Development | 1.5
Week 3 |  |  |  |  | Electrical Schematics | 5 | Build Prototype V1 | 5 | Video Log 3 | 1 | Week 3 | 20
[5 empty] | Design Mission Roundel | 2.5 | Build Prototype V1 | 5 | Curriculum Development | 1.5
4 |  |  |  |  | Electrical & Programming V1 | 3 | Build Prototype V1 | 5 | Video Log 4 | 1 | Week 4 | 19.5
| PSR#2 | March 6th | Re-evalutate Shopping List/Purchase | 1 | Electrical & Programming V1 | 3 | Build Prototype V1 | 5 | Curriculum Development | 1.5
5 |  |  |  |  | Prototyping/CAD V2 | 3 | Test Prototype V1 | 3 | Video Log 5 | 1 | Week 5 | 14.5
[5 empty] | Electrical V2 | 3 | Build Prototype V2 | 3 | Curriculum Development | 1.5
6 |  |  |  |  | Programming | 3 | Build Prototype V2 | 3 | Video Log 6 | 1 | Week 6 | 15.5
| PSR#3 | March 20th |  |  | Programming | 3 | Build Prototype V2 | 4 | Curriculum Development | 1.5
7 |  |  | Plan Mission Hike | 0.5 | Programming | 3 | Build V2 | 5 | Binder | 5 | Week 7 | 21.5
[7 empty] | Build V2 | 5 | Curriculum Development | 3
8 | [6 empty] | Test Build V2 | 5 | Video Log 7 | 1 | Week 8 | 10.5
| PSR#4 | April 10th |  |  |  |  | Finalize | 3 | Curriculum Development | 1.5
Break | [8 empty] | Mission Hike | 6 | Break | 11
[9 empty] | Post Mission Data | 5
9 | [10 empty] | Week 9 | 5
[9 empty] | Conclude Project - Assemble | 5
10 | [10 empty] | Week 10 | 0
| PSR#5 | April 24th | [6 empty] | Launch -> June?