## Template
|  | Phases: | Phase 1 name |  | Phase 2 name |  | Phase 3 name |  | Phase 4 name
|  |  | Hours | 1 | Hours | 1 | Hours | 1 | Hours | 1 | Total Hours | 4
Week
1 |  |  | Task | 1 | Task | 1 | Task | 1 | Task | 1 | Week 1 | 4
2 | [10 empty] | Week 2 | 0
| PSR#1 | Feb 14th
3 | [10 empty] | Week 3 | 0
Break | [10 empty] | Break | 0
4 | [10 empty] | Week 4 | 0
| PSR#2 | March 7th
5 | [10 empty] | Week 5 | 0
6 | [10 empty] | Week 6 | 0
| PSR#3 | March 21st
7 | [10 empty] | Week 7 | 0
8 | [10 empty] | Week 8 | 0
| PSR#4 | April 4th
9 | [10 empty] | Week 9 | 0
Break | [10 empty] | Break | 0
10 | [10 empty] | Week 10 | 0
| PSR#5 | April 25th

## Template with PreRelease
|  | Phases: | Research/Planning |  | Design/Prototyping |  | Production/Build |  | Launch/Community
|  |  | Hours | 14.5 | Hours | 41 | Hours | 22 | Hours | 26 | Total Hours | 103.5
Week
Pre | [10 empty] | PreRelease | 0
PrePSR
1 |  |  | Establish Hypothesis | 1 | [6 empty] | Week 1 | 6.5
|  |  | Research Near Space Satellites | 2 | Prototyping/CAD | 3 |  |  | Video Log 1 | 0.5
Break |  |  | Research Electrical Systems/Sensors | 0.5 | Prototyping/CAD | 3 |  |  |  |  | Break | 7.5
[5 empty] | Prototyping/CAD | 3 |  |  | Curriculum Development | 1
Week 2 |  |  |  |  | Finalize Design | 1 |  |  |  |  | Week 2 | 7
| PSR #1 | 2019-02-21 | Electrical Research | 1 | Approve Design | 2 | Electrical Research | 1 | Curriculum Development | 2
Week 3 |  |  | Create Shopping List | 1 | Flight Controller Familiarization | 1.5 |  |  |  |  | Week 3 | 9.5
[5 empty] | Design ASTRAIOS V2 | 5 |  |  | Curriculum Development | 2
4 |  |  |  |  | Design ASTRAIOS V2 | 5 |  |  |  |  | Week 4 | 8
| PSR#2 | March 6th |  |  | PICAXE Basic Code Review | 1 |  |  | Curriculum Development | 2
5 |  |  | Purchase Items | 1 | Design Mission Roundel | 2.5 |  |  | Video Log 2 | 1 | Week 5 | 11.5
[5 empty] | Flight Controller Mount CAD | 3 | Build ASTRAIOS V2 | 2 | Curriculum Development | 2
6 |  |  |  |  | Programming | 2 | Build ASTRAIOS V2 | 2 |  | 1 | Week 6 | 9.5
| PSR#3 | March 20th |  |  | Programming | 2 | Build ASTRAIOS V2 | 1 | Curriculum Development | 1.5
7 |  |  | Do Research on Flight Board and VBA | 2 | Modify Flight Code to work | 1 |  |  |  |  | Week 7 | 5
[5 empty] | Get sensor reading from flight board | 2
8 |  |  | Do Research on Flight Board and VBA | 2 | [6 empty] | Week 8 | 2
| PSR#4 | April 10th
Break |  |  | Plan Video Content | 2 | Convert Sensor Reading Values | 3 | Film Content | 4 |  |  | Break | 14
|  |  | Plan Video Content | 1 |  |  | Film Content | 4
9 |  |  | Possibly plan a quick build? | 1 |  |  | Edit Content | 8 | Present to Community ? | 8 | Week 9 | 23
[5 empty] | Make rough prototype of ASTRAIOS? | 1 |  |  | Conclude Project - Assemble | 5
10 | [10 empty] | Week 10 | 0
| PSR#5 | April 24th